## Quality Factors
*** Priority is calculated using Relative Weighting Approach
Benefit / Penalty Scale 1 (low) - 9 (high)
Quality Backlog
ID | Quality Factors | Category | Source | Sprint | Finished | Relative Benefit | Relative Penalty | Total Value | Value % | Estimate | Cost % | *** Priority
1 | 搭建Redmine发布环境build Redmine release environment |  | 系统system
2 | 编写测试纲要write the testing outline |  | 系统system
3 | 第一轮测试the first round of testing |  | 系统system
4 | 第二轮测试the second round of testing |  | 系统system
5 | 第三轮测试the third round of testing |  | 系统system
6
7
8
9
10
11
12
| TOTALS |  |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Quality Sprint Backlog
Sprint No. |  | Total Hours | Total Days | Hours/day
Sprint Period: |  | 320 | 10 | 32
ID | Quality Factors | WHO? | Status | Defects | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
1 | 搭建Redmine发布环境build Redmine release environment | all
2 | 编写测试纲要write the testing outline | all
3 | 第一轮测试the first round of testing | all
4 | 第二轮测试the second round of testing | all
5 | 第三轮测试the third round of testing | all
6
7
8
9
10
11
12
13
14
| Actual Hrs Remaining |  |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| Baseline Hrs Remaining |  |  |  | 288 | 256 | 224 | 192 | 160 | 128 | 96 | 64 | 32 | 0

## Tasks Tracking
Tasks Tracking
No. | To be analysed | To be tested | To be check | Finished | Tester | Todo 1 | Todo 2
John
Robin
Sonia
Jacky
Average
Count |  |  |  | 0

## Data Total
Quality factors coverage
Finished | Working | ToDo | Total
2 | 1 | 2 | 5
Defects status
Estimated | Find | Fixed | Open
60 | 26 | 0 | 26
Quality votes
Voter | Targets | Rate | Max
Koko | 94 | 80 | 100
Johnson | 94 | 85 | 100
Nanna | 94 | 88 | 100
Ivy | 94 | 90 | 100
Bill | 94 | 90 | 100
Average | 94 | 86.6 | 100
Defects Cause Analysis
Cause Root | Defects Number | percentage
Defect type A | 6 | 24%
Defect type B | 10 | 40%
Defect type C | 4 | 16%
Defect type D | 5 | 20%
Total | 25
Work Hours Estimated
Total Hours | Total Days | Hours per day
96 | 2 | 8
Date | Baseline Hrs Remaining | Actual Hrs Remaining
2009-05-12 | 131.2 | 286.4
2009-05-13 | 136 | 320
2009-05-14 | 140.8 | 353.6

## Quality Card
Redmine V0.8.3.stable (MySQL) Quality Card(5-22)
1、Quality factors coverage
2、Defects cause analysis
3、Quality votes
4、Quality votes
5、Burn down chart
6、Defects status
Project Quality Card
①
⑥
④
⑤
③
②