## Issues
# | Project | Tracker | Parent task | Status | Priority | Subject | Author | Assignee | Updated | Category | Target version | Start date | Due date | Estimated time | Spent time | % Done | Created | Closed | Related issues | Description | Team | Private | Watcher
880 | 03. Thử nghiệm Redmine | Bug |  | Resolved | Normal | Thuc hanh redmine | tannb | tannb | 2014-09-08 03:32 |  | Version 2.0 | 2014-08-27 | 2014-08-27 | 2 | 1 | 100% | 2014-08-27 07:06 |  |  | <p>Thu tao 1 task moi</p> |  | false
527 | 03. Thử nghiệm Redmine | Bug |  | Resolved | Normal | Form submit new issue | tungnm4 | tannb | 2014-09-04 11:52 |  | Version 2.0 | 2014-04-29 |  |  | 0 | 0% | 2014-04-29 10:00 |  |  | <p>Chức năng&nbsp;watchers kh&ocirc;ng c&oacute; n&uacute;t chọn &quot;Select all&quot; v&agrave; Deselect all&quot;.</p> <p>C&oacute; thể chọn group HW, SW, linh kiện,... được kh&ocirc;ng?</p> |  | false
526 | 03. Thử nghiệm Redmine | Feature |  | Pending | Normal | Add connection timeout feature | tungnm4 |  | 2014-12-13 09:42 |  | Version 2.0 | 2014-04-29 |  |  | 0 | 10% | 2014-04-29 09:58 |  |  | <p>Hiện chưa c&oacute; timeout khi user login v&agrave;o nhưng để l&acirc;y kh&ocirc;ng logout.</p> |  | false | hohieu tinmt tannb tungnm4 tungpt16
239 | 03. Thử nghiệm Redmine | Bug |  | New | Normal | Test pdf of lightbox plugin | tannb |  | 2014-09-03 03:02 |  | Version 2.0 | 2014-09-08 | 2014-09-10 | 5 | 0 | 0% | 2013-10-01 06:56 |  | Follows #236 | <p>Test pdf of lightbox plugin</p> |  | false
236 | 03. Thử nghiệm Redmine | Bug |  | Rejected | Normal | Test image of lightbox plugin | tannb | tannb | 2014-09-06 04:12 |  | Version 2.0 | 2014-09-02 | 2014-09-06 | 3 | 1 | 0% | 2013-10-01 03:48 |  | Precedes #239 | <p>Test image of lightbox plugin</p> |  | false