## Pending Task
S No | Pending Task(Summary) | Priority | Requirement Type | Issue Key | Issue Id | Requirement Clear Or Not | Dev ETA (with buffer time in days) | QA ETA | UAT Deployment Date | UAT Sign off Date | Prod Deployment Date | Status | Assigned Date | Dev assignee | Requirement Given By(Assignee) | Is ETA Extends | New ETA Dev (Extra Days) | New ETA QA (Extra Days) | Reason for extends | Description | UAT Deployment Date | UAT Sign off Date | Prod Deployment Date
1 | Option to check Deviation Status in Leasehub 2.0 | 1 | New Request | LH20-108 | 307963 | Yes | 2 days | 1 days | 2025-07-10 | 2025-07-11 | - | UAT Deployed | 2025-07-08 | Shubham | Alok Gaur
2 | CR- Foreclouser report and access new changes | 1 | New Request | LH20-65 | 296041 | Yes |  |  |  |  | - | In Progress |  | Abhishek | Hiral Sawant
3 | Schedule1 Creation & submission in Lease Hub post Vehicle Commencement |  | New Request | LH20-68 | 296565 | No |  |  |  |  | - | Not Started |  | Shubham | Smita Naik
4 | Deviation Matrix - Before onboarding of new client(ROA) | 1 | New Request | LH20-77 | - | Yes | 17 days | 5 days | 2025-07-30 | 2025-08-05 | - | In Progress | 2025-07-09 | Chandrashekhar | Vishal Sharma
5 | Deviation Matrix - Email notification and Approval link |  |  | LH20-112 | 308265 | Hold
6 | Payment frequency in Quote module, BVC chart (new, recal, renew, used car) |  |  | LH20-111 | 308261 | Hold
7 | Used car / Sale and Lease back quotation module (Client and Create Quotation) |  |  | LH20-110 | 308246 | Hold
8 | Lease recalculation quotation |  |  | LH20-109 | 308229
9 | Lease Renewal (extension) quote |  |  | LH20-104 | 303785 | Hold
10 | For M&M and group companies we need to include one field “Division” in VRL |  |  | LH20-78 | 300353 | P2 : Hold

## Daily Activity
S No | Date | Abhishek | Description | Dev Status | Chandrashekar | Description | Dev Status | Shubham | Description | Dev Status
1 | 2025-07-10 | 1.Making ETA for forecloser payoff/transfer changes | Need to sent Prajwal | Done | 1. Working with roa deviation module. | Working on UI Part 1. Ui input field . 2. Add Menu in dashboard. 3. add toggle on ro page | Done | 1. Working on option required to check deviations, where maker can check step by step status / progress along with approvers name. | - | Done
|  | 2.Will start working on the same changes from today( forecloser payoff/transfer changes) | 1.Add date range in filter so user can view daily progress | In- Progress | 2. Followup for odessa Loc utilized amount issue (Prod Bug) | Mail send and wating for the response. | Done | 2. Discuss to smita madam(Sale Team) for schedule one report | Mail send and wating for response | In Progress
|  | 3. Production Bug[Mail to odessa team] | Wating for response | Done | 3. Attend daily meeting (Vishal Sir) | - | - | 3. Attend daily meeting (Vishal Sir) | - | - | -
|  | 4. Attend daily meeting (Vishal Sir) | - | - | - |  |  | -
2 | 2025-07-11 | Production Bug[Mail to odessa team] | UAT deployed on 18-07-2025 from odessa team | Done | 1. Working with roa deviation module. | 1. Working on table structure | In - Progress | 1.Working on shedule one report UI enhancement. | - | In Progress
|  | Leave |  |  |  | 2. Create backend api( for : deviation calculation and assign) | To Do | 2. Follow- up to smita madam for BRD. | BRD Recevied | Done
[5 empty] | Followup for odessa Loc utilized amount issue (Prod Bug) | Response recievied from Jitendra sir , he loop another team for issue. |  | 3.Create release note for production build . | - | To do
[6 empty] | - | - | 4. Discuss to prajwal sir for CAB IT approval | Discuss with Jignesh Going on Monday | To do
[6 empty] | - | - | 5. Code merging into production branch. | After CAB IT approver | To do
[6 empty] | - | - | 6. Working on yesterday's feature bug.(raised today by testing team) | - | Done
[8 empty] | 7. Understanding and Discuss BRD with smita mam | - | To do

## Pending Production Bug
S No | Description | Issue key | Issue id | Status | Comment : 1 | Date | Comment :2 | Date
1 | Incorrect values reflecting under Line of Credit. |  |  | Pending | Mail send to dattu sir regarding solution . | 2025-07-10 | Looping another team for solution | 2025-07-11
2 | Rv % mismatch |  |  | Pending | Mail send to odessa team | 2025-07-10 | UAT deployed on 18-07-2025 from odessa team | 2025-07-10